## Sheet1
Phase | Duration | Goals | Key Features | Deliverables
Phase 1: MVP Foundation | Weeks 1–3 | Build basic functionality: meal planning, macro breakdown, grocery list | User profile, Meal database, Weekly planner, Nutrition breakdown, Grocery list | Working MVP with manual meal planning and data storage
Phase 2: Personalization & Training Sync | Weeks 4–6 | Introduce personalization and basic training integration | Training phase input, Meal suggestions, User targets, Saved plans | Dynamic plans based on training load and user goals
Phase 3: Premium & Monetization | Weeks 7–10 | Add monetizable features and test payment flow | Premium tier, Paid meal packs, Export features, Affiliate links | Revenue-ready version with at least one premium feature
Phase 4: Community, AI & Expansion | Weeks 11+ | Increase engagement and integrate AI | AI meal generator, Community sharing, Notifications, Health app sync | Engaged user base with smart and social features